## Sheet1
Defect ID | Title | Description | Steps to Reproduce | Root Cause | Fix Applied | Preventive Action Taken
DEF-001 | Viewer able to access workflow edit | Viewer role was able to open workflow edit screen, which should be blocked | Login as viewer, go to workflows, click on edit icon | Role-based access check missing in UI layer | Added role check in UI and API for edit button and endpoint | Added role-based access test cases in UI and API test suites
DEF-002 | Workflow approval fails with 500 | Approving a workflow returns internal server error | Login as admin, create workflow, approve it immediately | Backend service was not handling null status field | Added null check and default status in backend approval logic | Added API test for approval with missing status
DEF-003 | Invalid token not handled gracefully | API with invalid token returns HTML error page instead of JSON | Send API request with invalid token using Postman | Global exception handler not catching token errors | Updated exception handler to return proper JSON response for auth errors | Added API error handling test cases for invalid and expired tokens